| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/22 29 October 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

2018 CONSOLIDATED PROJECT COMPLETION REPORT

- Background

# The issue of outstanding projects completion reports (PCRs) has been addressed by the Executive Committee at each of its meetings. At the 81st meeting, the Executive Committee inter alia urged bilateral and implementing agencies (IAs) to submit to the 82nd meeting the backlog of PCRs for multi-year agreements (MYAs) and individual projects listed in documents UNEP/OzL.Pro/ExCom/81/11 and Corr.1, and if the PCRs due were not submitted, to provide the reasons for not doing so and the schedule for submission. The Committee also urged cooperating IAs to complete their portions of PCRs to allow the lead IA to submit them according to the schedule (decision 81/25(b) and (c)).

# Pursuant to decision 81/25(b) and (c), the Senior Monitoring and Evaluation Officer (SMEO) sent a preliminary list of all PCRs due to bilateral and IAs on 25 July 2018, and an updated list on 19 October 2018, after the progress reports were submitted.

- MYA PCRs received

# Of the 184 MYA completed, bilateral and IAs had submitted 154 PCRs, prior to the 82nd meeting, with an outstanding balance of 30 as shown in Table 1. The list of the 11 PCRs submitted after the 81st meeting is attached in Annex I to the present report.

# Table 1. Overview of MYAs PCRs

| Lead agency | Completed | Received prior to the 81st meeting | Received after the 81st meeting | Outstanding |
| --- | --- | --- | --- | --- |
| Canada | 3 | 2 | 0 | 1 |
| France | 5 | 0 | 3 | 2 |
| Germany | 10 | 8 | 0 | 2 |
| Japan | 1 | 1 | 0 | 0 |
| UNDP | 35 | 23 | 5 | 7* |
| UNEP | 58 | 55 | 0 | 3 |
| UNIDO | 49 | 45 | 2 | 2 |
| World Bank | 23 | 9 | 1 | 13 |
| Total | 184 | 143 | 11 | 30 |

# * The outstanding PCR for stage I of the HCFC phase-out plan for China (solvent sector plan) is due no later than the last meeting in 2019.

# An analysis of the aggregated fund disbursed, ODS phased out and delay in the completion of the 11 MYA PCRs is summarized in Table 2.

# Table 2. Overview of the budget, ODS phased out and delay of MYAs submitted after the 81st meeting

| Lead agency | MYA funds (US$) |  | ODP tonnes phase out |  | Average delay (months) |
| --- | --- | --- | --- | --- | --- |
|  | Approved | Disbursed | Approved | Actual |  |
| France | 903,275 | 903,275 | 141.1 | 120.1 | 9.33 |
| UNDP | 43,209,545 | 38,113,007 | 574.5 | 446.2 | 1.40 |
| UNIDO | 1,089,706 | 1,325,055 | 48.0 | 48.0 | 25.00 |
| World Bank | 18,837,727 | 18,694,380 | 1,954.2 | 1,954.2 | 30.00 |
| Total | 64,040,253 | 59,035,717 | 2,717.8 | 2,568.5 | 16.43 |

Reasons for delays

# Project design and planning are frequent reasons for delays. In a chiller project, the delay was due to a prolonged identification of beneficiaries. In one of the projects, the time needed to identify a partner to carry out trainings created delays, while in another it was due to the approval of regulations.

# Inadequate staffing at the government level is another recurring reason for delay. In smaller countries, the scarcity of staff affects projects, as demonstrated by one National Ozone Officer (NOO) also being the Government’s Chief Meteorologist, and therefore being unable to dedicate sufficient time to project implementation. In another project, the lack of available legal staff slowed the adoption of norms. Government changes also affect projects as one case demonstrated by a ministerial reorganization that affected the timely expenditure of funds.

# Fund-related issues are a repeated cause for delays. In one instance the agency mentioned the long process for acceptance of international grants, whereas two other agencies imputed the delays respectively to the signing and the finalization of the agreement with the government.

# The specific delays at the enterprise level were attributed to the restructuration of the training, due to safety requirements and incomplete documentation and invoices.

# Lessons learned

# Coordination, frequent communication and collaboration between all stakeholders (i.e., governmental agencies, IAs, industry associations and academia), from design to implementation, are vital for a successful implementation of projects. A NOU specifically stressed the importance of a sound coordination between institutional strengthening and the HPMP. One country mentioned the essential pre-established coordination between agencies involved in the project to enforce regulations, which is exemplified by another country’s successful creation of an inter-ministerial commission to manage ODS phase-out.

# Regulations and standards should be in place as early as possible as they often require extensive time to establish and/or modify. According to an IA, the licensing requirements for imported pre-blended polyols proved an efficient tool to monitor consumption trends and identifying small and medium-size ODS users, some of which were previously unknown. Another agency mentioned the importance of creating a project implementation manual, which can be updated along the way, allowing for an improved monitoring, while serving as an interactive tool of communication with the beneficiaries. Improved ties between customs and the environmental agency where praised by a NOU.

# In the refrigeration and air-conditioning (RAC) sector, one recurring lesson has been the importance of the refrigeration association as a key part to successful and sustainable projects (e.g., namely by encouraging the industry to be involved in training, recovery, recycling and reclamation (RRR) and incentives practices). However, assistance should be provided to these associations at the inception phase. In one country they managed to phase-out CFCs three years prior to the deadline and the relationship between the NOU and the industry is now helping all ODS phase out-related activities.

# Training and technical assistance, are important to be planned as early as possible, especially when involving the introduction of flammable or toxic alternatives. One country noted the importance of combining worker safety to the development of an environmental management. Another country mentioned the importance of providing the training in the local language.

# The sectorial approach to phasing-out ODS has proven effective, according to a country that linked its quick adoption of the alternative and an early phase-out of HCFC-141b, to awareness raising and the agency’s cooperation. Coordination between activities in different sectors has been mentioned as an important factor to sustainability and public awareness towards ozone protection. One country evaluated that the success of implementation was due, in part, to the nationwide environmental awareness campaign.

# An open and participatory selection of the beneficiary enterprises proved efficient. In one case, it led enterprises to be more committed to the process, dedicating time and effort, which translated to long-term sustainability of the project.

# Financial barriers were mentioned by one IA, as it witnessed beneficiary enterprises financing the equipment before signing the contract with the supplier, constraining them to find counterpart funding for the items not funded. This proves additionally challenging for small and medium-sized enterprises (SMEs). Low participation of enterprises was due inter alia to adverse economic situations, relatively temperate climate and the low cost of electricity, which lowers their perception of the necessity for an updated and energy efficient technology.

- Individual PCRs received

# Of the total 1,855 investment projects that have been completed, bilateral and IAs had submitted 1,846 PCRs, with a balance of nine outstanding PCRs as shown in Table 3.

Table 3. PCRs submitted for investment projects

| Agency | Completed | Received prior 81st meeting | Received after the 81st meeting | Outstanding |
| --- | --- | --- | --- | --- |
| France | 14 | 13 | 0 | 1 |
| Germany | 20 | 19 | 0 | 1 |
| Italy | 11 | 10 | 0 | 1 |
| Japan | 6 | 6 | 0 | 0 |
| Spain | 1 | 1 | 0 | 0 |
| United Kingdom of Great Britain and Northern Ireland | 1 | 1 | 0 | 0 |
| United States of America | 2 | 2 | 0 | 0 |
| UNDP | 895 | 893 | 1 | 1 |
| UNIDO | 448 | 446 | 2 | 0 |
| World Bank | 457 | 452 | 0 | 5 |
| Total | 1,855 | 1,843 | 3 | 9 |

# Of the 1,301 non-investment projects that have been completed, bilateral and IAs had submitted 1,113 PCRs, with a balance of 188 outstanding PCRs as shown in Table 4.

Table 4. PCRs submitted for non-investment projects

| Agency | Completed | Received prior 81st meeting | Received after the 81st meeting | Outstanding |
| --- | --- | --- | --- | --- |
| Canada | 57 | 56 | 0 | 1 |
| France | 34 | 14 | 3 | 17 |
| Germany | 62 | 56 | 0 | 6 |
| Italy | 1 | 0 | 1 | 0 |
| Japan | 17 | 14 | 1 | 2 |
| Portugal | 1 | 0 | 0 | 1 |
| UNDP | 296 | 278 | 2 | 16 |
| UNEP | 539 | 430 | 3 | 106 |
| UNIDO | 159 | 123 | 6 | 30 |
| World Bank | 45 | 36 | 0 | 9 |
| Others | 90 | 90 | 0 | 0 |
| Total | 1,301 | 1,097 | 16 | 188 |

# The list of 19 investment and non-investment PCRs received after the 81st meeting is contained in Annex II to the present document; the aggregated results relevant to disbursement, actual phase-out and delays are shown in Table 5.

# Table 5. Overview of the budget, ODS phased out and delay of individual projects submitted after the 81st meeting

| Agency | Number of projects | Funds (US$) |  | ODP tonnes phase out |  | Average delay (months) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Approved | Disbursed | Approved | Actual | Duration | Delays |
| France | 3 | 323,552 | 235,120 | 91.5 | 10.9 | 61.67 | 25.67 |
| Italy | 1 | 132,743 | 132,743 | 2.2 | 2.2 | 23.00 | 0.0 |
| Japan | 1 | 700,000 | 699,896 | 0.0 | 0.0 | 135.00 | 99.00 |
| UNDP | 3 | 1,504,996 | 1,465,225 | 83.8 | 83.8 | 93.67 | 27.67 |
| UNEP | 3 | 90,000 | 85,183 | 0.4 | 0.0 | 21.00 | 19.00 |
| UNIDO | 8 | 2,751,291 | 2,618,167 | 91.46 | 96.88 | 66.87 | 34.27 |
| Total | 19 | 5,076,536 | 4,792,139 | 187.4 | 119.4 | 65.49 | 33.93 |

Reasons for delays

# Different funding cycles and preparation phases with complementary activities in the same country made projects coordination and implementation impractical, as they were implemented independently from one another. The delays it created were solved by a streamlined approach to project planning. The expiration of the financial agreement with the bilateral agency impeded one project implementation. Two PCRs mentioned delays in securing co-financing, while a third one mentioned the incompatibility between the financing model and the country’s reality.

# Delays, in two countries, were due to the lack of available and qualified experts. Rigorous rules and terms of references to hire professionals, at the enterprises level, might favour quality but may create lengthy delays in contracting them, especially in low-volume consuming (LVC) countries.

# The institutional configuration of project management (i.e., NOUs and PMUs) is crucial to a successful and timely project implementation. Limited powers of the NOU made regulation approval difficult in one country, creating delays so substantial that the project was closed. The numerous commitments of an NOO, the retirement of another and the difficult communication between a NOU and the IA were also mentioned as causes for delays.

# Delays in launching a project produced a domino effect delaying it furthermore by reprogramming awareness raising campaigns and training. Procurement and equipment delivery delays were mentioned in three cases, whilst the approval of a terminal phase-out management plan delayed the implementation of refrigerant management plans activities already in motion.

# Lengthy legislation processes, in two countries, were mentioned as the main cause for delay and one country specified that the that approval of regulatory measures took three years.

# Technical problems also delayed projects. In an ODS destruction project, they were due to complications in synchronizing the collection and shipment of ODS, while the implementation of a refrigerant management plan project mentioned the restructuring of the training institute.

# External factors significantly delaying projects were the unstable political situation, the change of government and embargoes, all of which impacted drastically the flow of capital.

# Lessons learned

# Lessons learned from the individual PCRs relate, inter alia, to: financial issues; cooperation and coordination among all stakeholders; recycling and recovery issues; project implementation issues; and the transfer of technology.

# One chiller demonstration project mentioned the benefits gained from the lessons learned in previous CFC national phase-out plan projects, and the successful readjustment of administrative and financial processes that contributed to the achievement of high-quality outcomes with economic and environmental impacts.

# Various individual PCRs emphasized on the necessity for regular coordination between the relevant stakeholders. A deficient coordination affected a project that was later abandoned by the enterprise that did not attain critical mass and the economy of scale necessary to sustain the technical requirement of manufacture. Experience has shown that full involvement of local experts is needed for the successful preparation, design and implementation of the activities. One NOO hired a local customs officer as consultant, a practice they highly recommend to replicate. Verification reports praised the importance of an independent inquiry and collaboration with all stakeholders, especially with customs, as well as the establishment of an electronic platform for licenses and quotas.

# Technical assistance projects emphasised the need to involve the industry’s association, increase the awareness raising initiatives and training, to ensure sustainability of the alternative and a larger acceptance of the alternative by end-users. Conversely, the inadequate and irregular supply of proper equipment impeded a project.

# ODS management and disposal demonstration projects highlighted the need of early obtainment of import/export and transit permits to avoid delays caused by the lengthy processes affecting synchronization of shipments and destruction of waste from different countries. A mandatory record keeping for servicing companies, RRR centres and operators of refrigeration, air-conditioning and firefighting equipment will provide the necessary information on installed equipment, capacities, refrigerant type and leakage rates. These projects questioned the financial feasibility of separating ODS and non-ODS-based refrigerant prior to destruction; emphasized the need to select destruction facilities based on geographical and technical criteria; mentioned the need for targeted inspection to comply with the RRR scheme for the collection of ODS waste; and the need to broaden the training of environment inspectors (i.e., to inspect different types of refrigeration and air-conditioning equipment, to review equipment log-books and be aware of commonly used refrigerants and related safety precautions).

# Simultaneous implementation of projects and the rotation of staff at the NOO affect the efficiency of project implementation. One country suggested initiating projects only following the completion of existing ones, and another noted that project design should be kept as simple as possible even if the issues are complex.

# One NOU stressed the importance of technology transfer to ensure the introduction of adequate technology tailored to country-specific needs. The agreement between the bilateral and IA favoured an innovative and commercially viable strategy for replacing CFC-based chillers by including the transfer of green technology, the creation of a working fund mechanism, the management of CFC stockpiles, and the dissemination of awareness-raising material to stakeholders (i.e., chiller operators, end-users and government personnel).

# Outstanding MYA PCRs and PCRs

# The Secretariat appreciates the actions by some of the bilateral and IAs to address the backlog of outstanding PCRs.

# The Secretariat stressed the issue of submission of PCRs for stage I of the HPMP to the bilateral and IAs, as these are mandatory for the approval of the second stage. Annexes III, IV and V respectively list the outstanding PCRs. The high number of outstanding individual PCRs is due, in part, to the ODS survey projects completed this year, contained in the second table of Annex III. The Secretariat also notes that, in line with decision 81/25(b), the World Bank did not provide reasons for not submitting PCRs according to their schedule.

# Starting in 2019, the schedule for the submission of outstanding PCRs, used as the target for the evaluation of the performance indicators, will include all the projects that have been completed six months or more after the completion date reported on the progress report (as of December of the previous year). This schedule will extend over the full calendar year.

# RECOMMENDATION

# The Executive Committee may wish:

## To note the 2018 consolidated project completion report (PCR) contained in document UNEP/OzL.Pro/ExCom/82/22;

## To urge bilateral and implementing agencies to submit to the 83rd meeting PCRs for multi-year agreements (MYAs) and individual projects that were due, and if they were not going to submit, to provide the reasons for not doing so;

## To urge lead and cooperating agencies to closely coordinate their work in finalizing their portion of PCRs to allow the lead implementing agency to submit the completed PCRs according to the schedule;

## To urge bilateral and implementing agencies to enter clear, well written and thorough lessons when submitting their PCRs; and

## To invite all those involved in the preparation and implementation of MYAs and individual projects to take into consideration the lessons learned from PCRs, if relevant, when preparing and implementing future projects.

## Annex I

MYA PCRs RECEIVED

| Country | MYA Sector | Lead Agency | Cooperating Agencies |
| --- | --- | --- | --- |
| Argentina | CFC phase out plan | World Bank |  |
| Armenia | HCFC phase out plan (stage I) | UNDP | UNEP |
| China | HCFC phase out plan (stage I) | UNDP |  |
| Colombia | HCFC phase out plan (stage I) | UNDP | UNEP |
| Guatemala | Methyl bromide | UNIDO |  |
| India | HCFC phase out plan (stage I) | UNDP | UNEP/Germany |
| Kenya | CFC phase out plan | France |  |
| Malaysia | HCFC phase out plan (stage I) | UNDP |  |
| Seychelles | CFC phase out plan | France |  |
| Uganda | ODS phase out plan | France |  |
| Vietnam | HCFC phase out plan (stage I) | World Bank |  |

Annex II

INDIVIDUAL PCRs RECEIVED

| Project Number | Agency | Project Title |
| --- | --- | --- |
| ETH/REF/44/TAS/14 | France | Refrigerant management plan update |
| UGA/REF/44/TAS/11 | France | Refrigerant management plan update |
| URT/REF/46/TAS/18 | France | Refrigerant management plan update |
| TUN/FUM/73/TAS/62 | Italy | Technical assistance for the final phase-out of methyl bromide in the palm dates sector |
| AFR/REF/48/DEM/35 | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) |
| BRA/REF/47/DEM/275 | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers. |
| PAK/ARS/56/INV/71 | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs |
| BGD/SEV/75/TAS/46 | UNDP | Survey of ODS alternatives at the national level |
| BHU/PHA/73/TAS/22 | UNEP | Verification report on the implementation of the HCFC phase-out management plan |
| MDV/PHA/73/TAS/26 | UNEP | Verification report on the implementation of the HCFC phase-out management plan |
| MON/PHA/71/TAS/21 | UNEP | Verification report on the implementation of the HCFC phase-out management plan |
| AFR/REF/48/DEM/37 | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) |
| EGY/FUM/74/TAS/123 | UNIDO | Technical assistance on two alternatives to methyl bromide in the palm date sector |
| EUR/DES/69/DEM/14 | UNIDO | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region |
| IRQ/FUM/62/INV/13 | UNIDO | Technical assistance for alternatives to methyl bromide |
| SUD/FUM/73/TAS/36 | UNIDO | Technical assistance for the final phase-out of methyl bromide in the post harvest sector |
| TUN/FUM/73/TAS/63 | UNIDO | Technical assistance for the final phase-out of methyl bromide in the palm dates sector |
| YUG/SEV/74/TAS/45 | UNIDO | Survey of ODS alternatives at the national level |
| ZAM/FUM/56/INV/21 | UNIDO | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses |

Annex III

OUTSTANDING INDIVIDUAL PCRs

| Country | Code | Lead agency and cooperating agency |
| --- | --- | --- |
| Africa Region | AFR/REF/48/DEM/36 | France |
| Africa Region | AFR/DES/68/TAS/41 | France |
| Albania | ALB/PHA/71/TAS/27 | UNIDO |
| Argentina | ARG/ARS/56/INV/159 | World Bank |
| Argentina | ARG/REF/18/INV/39 | World Bank |
| Asia and Pacific Region | ASP/REF/69/DEM/56 | UNEP |
| Asia and Pacific Region | ASP/REF/69/DEM/57 | UNIDO |
| Bahamas | BHA/PHA/71/TAS/19 | UNEP |
| Barbados | BAR/PHA/75/TAS/25 | UNEP |
| Central African Republic | CAF/REF/34/TAS/10 | France |
| Central African Republic | CAF/REF/34/TAS/11 | France |
| Central African Republic | CAF/REF/34/TRA/08 | France |
| Central African Republic | CAF/REF/34/TRA/09 | France |
| China | CPR/SOL/64/DEM/506 | Japan |
| China | CPR/DES/67/DEM/521 | Japan |
| China | CPR/DES/67/DEM/520 | UNIDO |
| China | CPR/ARS/51/INV/447 | World Bank |
| China | CPR/PRO/69/TAS/531 | World Bank |
| Colombia | COL/SEV/75/TAS/99 | Germany |
| Costa Rica | COS/REF/76/DEM/55 | UNDP |
| Costa Rica | COS/PHA/75/TAS/54 | UNDP |
| Dominican Republic | DOM/REF/74/TAS/57 | UNDP |
| Ecuador | ECU/PHA/77/TAS/63 | UNIDO |
| Ethiopia | ETH/PHA/75/TAS/25 | UNEP |
| Europe Region | EUR/DES/69/DEM/13 | UNEP |
| Gambia (the) | GAM/PHA/71/TAS/27 | UNEP |
| Georgia | GEO/PHA/75/TAS/38 | UNDP |
| Ghana | GHA/DES/63/DEM/33 | UNDP |
| Global | GLO/SEV/47/TAS/269 | Portugal |
| Global | GLO/SEV/63/TAS/309 | World Bank |
| Haiti | HAI/PHA/73/TAS/19 | UNEP |
| India | IND/ARS/56/INV/424 | Italy |
| India | IND/ARS/56/INV/423 | UNDP |
| India | IND/ARS/56/TAS/425 | UNEP |
| India | IND/HAL/34/INV/315 | World Bank |
| Indonesia | IDS/ARS/56/TAS/184 | World Bank |
| Jordan | JOR/FUM/29/INV/54 | Germany |
| Jordan | JOR/PHA/38/INV/77 | World Bank |
| Kuwait | KUW/REF/37/TAS/06 | UNEP |
| Kuwait | KUW/REF/37/TRA/03 | UNEP |
| Kuwait | KUW/REF/37/TRA/04 | UNEP |
| Kyrgyzstan | KYR/PHA/77/TAS/38 | UNDP |
| Lao People's Democratic Republic | LAO/REF/34/TAS/06 | France |
| Lao People's Democratic Republic | LAO/REF/34/TRA/03 | France |
| Lao People's Democratic Republic | LAO/REF/34/TRA/04 | France |
| Latin American Region | LAC/SEV/51/TAS/38 | Canada |
| Lebanon | LEB/REF/28/TAS/29 | France |
| Lebanon | LEB/REF/23/TAS/21 | France |
| Lesotho | LES/PHA/74/TAS/18 | Germany |
| Madagascar | MAG/REF/29/TAS/05 | France |
| Madagascar | MAG/REF/47/TAS/12 | France |
| Madagascar | MAG/REF/29/TRA/02 | France |
| Madagascar | MAG/REF/29/TRA/03 | France |
| Malawi | MLW/PHA/71/TAS/35 | UNEP |
| Mauritius | MAR/SEV/75/TAS/24 | Germany |
| Mauritius | MAR/PHA/75/TAS/25 | Germany |
| Mexico | MEX/DES/63/DEM/155 | France |
| Mexico | MEX/DES/63/DEM/154 | UNIDO |
| Morocco | MOR/REF/23/TAS/17 | France |
| Myanmar | MYA/PHA/73/TAS/16 | UNEP |
| Namibia | NAM/PHA/74/TAS/21 | Germany |
| Nepal | NEP/DES/59/TAS/27 | UNEP |
| Niger (the) | NER/PHA/71/TAS/29 | UNIDO |
| Papua New Guinea | PNG/SEV/75/TAS/14 | Germany |
| Republic of Moldova | MOL/PHA/73/TAS/30 | UNDP |
| Rwanda | RWA/PHA/75/TAS/25 | UNEP |
| Serbia | YUG/PHA/71/TAS/42 | UNIDO |
| Sri Lanka | SRL/PHA/71/TAS/45 | UNDP |
| Syria | SYR/REF/29/TRA/49 | UNEP |
| Syrian Arab Republic | SYR/REF/29/INV/56 | France |
| Syrian Arab Republic | SYR/REF/29/TAS/51 | UNEP |
| Syrian Arab Republic | SYR/REF/29/TRA/47 | UNEP |
| The Former Yugoslav Republic of Macedonia | MDN/PHA/75/TAS/38 | UNIDO |
| Trinidad and Tobago | TRI/FUM/65/TAS/28 | UNEP |
| Turkey | TUR/DES/66/DEM/99 | UNIDO |
| Uganda | UGA/PHA/71/TAS/18 | UNEP |
| Yemen | YEM/REF/37/TAS/16 | UNEP |
| Yemen | YEM/REF/37/TAS/19 | UNEP |
| Yemen | YEM/REF/37/TRA/17 | UNEP |
| Yemen | YEM/REF/37/TRA/18 | UNEP |

ODS SURVEY PROJECTS

| Agency | Countries |
| --- | --- |
| UNDP | Costa Rica, Cuba, Dominican Republic, El Salvador, Panama, Paraguay, Peru, Republic of Moldova |
| UNEP | Afghanistan, Algeria, Angola, Antigua and Barbuda, Armenia, Bahamas, Bahrain, Barbados, Belize, Benin, Bhutan, Botswana, Brunei Darussalam, Burkina Faso, Burundi, Cambodia, Cape Verde, Chad, Comoros, Congo, Cook Island, Cote D'Ivoire, Democratic Republic of Congo, Djibouti, Equatorial Guinea, Eritrea, Eswatini, Ethiopia, Federated States of Micronesia, Gabon, Gambia (the), Ghana, Grenada, Guinea, Guinea-Bissau, Guyana, Iraq, Jamaica, Kenya, Kiribati, Kuwait, Kyrgyzstan, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Maldives, Mali, Marshall Islands, Mongolia, Mozambique, Myanmar, Namibia, Nauru, Nepal, Nigeria, Niue, Pakistan, Palau, Rwanda, Saint Lucia, Samoa, Sao Tome and Principe, Saudi Arabia, Senegal, Seychelles, Sierra Leone, Solomon Island, Sri Lanka, Sudan, Suriname, Timor Leste, Togo, Tonga, Trinidad and Tobago, Turkmenistan, Tuvalu, United Republic of Tanzania, Vanuatu, Zambia, Zimbabwe |
| UNIDO | Albania, Argentina, Bahrain, Bolivia (Plurinational State of), Bosnia and Herzegovina, Cameroon, Chile, Georgia, Honduras, Kuwait, Libya, Mexico, Nicaragua, Niger (the), Sudan, the Former Yugoslav Republic of Macedonia, Tunisia, Turkey, Uganda, Uruguay, Venezuela (Bolivarian Republic of) |
| World Bank | Jordan, Philippines, Thailand, Vietnam |

Annex IV

OUTSTANDING PCRs BY DECISION

| Country | MYA Sector/Title | Lead agency and Cooperating agency |
| --- | --- | --- |
| Chile | HCFC phase out plan (stage I) | UNDP/UNEP |
| China | HCFC phase out plan (stage I) – PU foam | World Bank |
| Dominican Republic | HCFC phase out plan (stage I) | UNDP/UNEP |
| Iraq | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC‑11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | UNIDO |
| Jordan | HCFC phase out plan (stage I) | UNIDO/World Bank |
| Venezuela (Bolivarian Republic of) | HCFC phase out plan (stage I) | UNIDO |
| Yemen | ODS phase out plan | UNEP/UNIDO |

Annex V

OUTSTANDING MYA PCRs

| Country | MYA Sector/Title | Lead agency and Cooperating agency |
| --- | --- | --- |
| Angola | HCFC phase out plan (stage I) | UNDP |
| Argentina | Production CFC | World Bank |
| Bahamas | CFC phase out plan | World Bank |
| Bahrain | CFC phase out plan | UNEP/UNDP |
| Bolivia (Plurinational State of) | ODS phase out plan | Canada/UNDP |
| China | Solvent | UNDP |
| China | CFCs/CTC/Halon Accelerated Phase-Out Plan | World Bank/United States |
| China | Foam | World Bank |
| China | Halon | World Bank |
| China | Process agent (phase I) | World Bank |
| China | Process agent (phase II) | World Bank |
| China | Production CFC | World Bank |
| India | CFC phase out plan (including Foam, Refrigeration Manufacturing and Refrigeration Servicing) | Germany |
| India | Accelerated production CF | UNDP/World Bank |
| India | CTC phase out plan | World Bank/France/Germany/Japan/ UNDP/UNIDO |
| India | Production CFC | World Bank |
| Iran (Islamic Republic of) | CFC phase out plan - MAC R&R | France |
| Kuwait | ODS phase out plan | UNEP/UNIDO |
| Lao People’s Democratic Republic | CFC phase out plan | France |
| Lebanon | HCFC phase out plan (stage I) | UNDP |
| Moldova, Republic of | HCFC phase out plan (stage I) | UNDP |
| Pakistan | HCFC phase out plan (stage I) | UNIDO/UNEP |
| Peru | HCFC phase out plan (stage I) | UNDP/UNEP |
| Philippines | HCFC phase out plan (stage I) | UNEP/Japan/UNIDO |
| Philippines | CFC phase out plan | World Bank/Sweden/UNEP |
| Uruguay | HCFC phase out plan (stage I) | UNDP |
| Venezuela (Bolivarian Republic of) | Production CFC | World Bank |
| Vietnam | Methyl bromide | World Bank |
| Yemen | Methyl bromide | Germany |

Lessons learned from MYA PCRs can be found on the MYA PCR lessons learned database: http://www.multilateralfund.org/myapcr/search.aspx

Excluding project preparation, country programmes, multi-year projects, networking, clearing-house activities, and institutional strengthening projects.

Including PCRs completed and received from the following countries: Australia (25), Austria (1), Czech Republic (2), Denmark (1), Finland (5), Israel (2), Poland (1), South Africa (1), Spain (4), Sweden (5), Switzerland (3), and United States of America (40).

Lessons learned from the individual PCRs can be found in the PCR lessons learned database: http://www.multilateralfund.org/pcrindividual/search.aspx

The SMEO stressed once again at the Inter-agency coordination meeting (Montreal, 4-6 September 2018) the importance to submit all outstanding PCRs, noting that many projects have been completed several years ago, and that progress and financial reports on completed projects have to be submitted until the PCRs are submitted, which increases the workload of the Executive Committee, the IAs and the Secretariat.

Decision 81/29.