| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/88/4 21 octobre 2021 FRANÇAIS ORIGINAL: ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-huitième réunion

Montréal, 15 – 19 novembre 2021

# RAPPORT SUR LES SOLDES ET LA DISPONIBILITÉ DES RESSOURCES

# Introduction

# Le présent document contient un résumé des ajustements financiers indiqués par les agences bilatérales et les agences d’exécution et approuvés par le Secrétariat. Comme l’exigent les décisions 28/7 et 56/2 c), il comprend des données statistiques sur les projets pour lesquels les agences bilatérales et les agences d’exécution détiennent des soldes au-delà de la période autorisée de 12 mois après l’achèvement du projet. Il traite des soldes de projets à restituer en vertu des décisions pertinentes (appelés « projets par décision » dans ce document). Conformément à la décision 41/92 b), ce document présente également le montant des ressources, en espèces, à la disposition du Comité exécutif, tel qu’il figure dans l’état des contributions et des décaissements, ainsi qu’une recommandation.

# Le présent document comprend les quatre annexes suivantes :

Annexe I	Sommes détenues par les agences bilatérales et d’exécution pour les projets achevés

Annexe II 	Sommes détenues par les agences bilatérales et d’exécution pour les projets par décision

Annexe III 	Sommes détenues par les agences bilatérales et d’exécution pour les projets financés au titre des contributions volontaires supplémentaires

Annexe IV	Sommes retournées par les agences bilatérales et d’exécution pour les projets achevés, par décision, et financés au titre des contributions supplémentaires

# Les annexes II et III fournissent les explications concernant les retards dans le décaissement des sommes engagées ou la restitution des sommes non engagées.

Sommes à retourner à la 88e réunion

# La somme totale à restituer pour les projets achevés, par décision et financés au titre des contributions volontaires supplémentaires est de 6 322 577 $US (2 339 $US par les agences bilatérales et 6 320 238 $US par les agences d’exécution).

Sommes à retourner par les agences d’exécution

# Comme l’indique le tableau 1, les sommes totales à restituer par les agences d’exécution s’élèvent à 6 320 238 $US.

# Tableau 1. Sommes à retourner à la 88eréunion ($US)

| Agence | Coût du projet | Coûts d’appui d’agence | Coût total |
| --- | --- | --- | --- |
| PNUD | 2 261 506 | 168 607 | 2 430 113 |
| PNUE | 3 165 404 | 241 892 | 3 407 296 |
| ONUDI | 36 947 | 2 678 | 39 625 |
| Banque mondiale | 0 | 443 204 | 443 204 |
| Total | 5 463 857 | 856 381 | 6 320 238 |

# Le tableau 2 présente des renseignements sur les soldes des projets achevés, par décision et financés au titre des contributions volontaires supplémentaires qui sont retenus par les agences d’exécution.

Tableau 2. Soldes des projets achevés, par décision et financés au titre des contributions volontaires supplémentaires retenus par les agences d’exécution (y compris les coûts d'appui d’agence)

| Année d’achèvement | PNUD |  | PNUE |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nombre | ($US) | Nombre | ($US) | Nombre | ($US) | Nombre | ($US) |
| Projets achevés il y a plus de deux ans |  |  |  |  |  |  |  |  |
| 2017 | 1 | 21 740 | 0 | 0 | 0 | 0 | 1 | 21 740 |
| 2018 | 1 | 1 787 | 0 | 0 | 0 | 0 | 1 | 1 787 |
| 1er janv au 31 oct. 2019 | 1 | 2 246 | 0 | 0 | 0 | 0 | 1 | 2 246 |
| Sous-total | 3 | 25 773 | 0 | 0 | 0 | 0 | 3 | 25 773 |
| Projets achevés il y a moins de deux ans |  |  |  |  |  |  |  |  |
| 1er nov. au 31 déc. 2019 | 13 | 842 341 | 0 | 0 | 0 | 0 | 13 | 842 341 |
| 2020 | 20 | 3 218 499 | 2 | 18 257 | 11 | 1 235 473 | 33 | 4 472 229 |
| Sous-total | 33 | 4 060 840 | 2 | 18 257 | 11 | 1 235 473 | 46 | 5 314 570 |
| Total | 36 | 4 086 613 | 2 | 18 257 | 11 | 1 235 473 | 49 | 5 340 343 |
| Projets par décision (en cours) |  |  |  |  |  |  |  |  |
|  | 1 | 135 001 | 2 | 116 344 | 0 | 0 | 3 | 251 345 |
| Contributions volontaires supplémentaires |  |  |  |  |  |  |  |  |
|  | 3 | 22 223 | 0 | 0 | 0 | 0 | 3 | 22 223 |
| Total | 40 | 4 243 837 | 4 | 134 601 | 11 | 1 235 473 | 55 | 5 613 911 |

Sommes à retourner par les agences bilatérales

# Les fonds totaux à restituer par les agences bilatérales s'élèvent à 2 339 $US, soit 2 070 $US, plus les coûts d’appui d’agence de 269 $ US pour l'Australie.

# Le Japon retient les soldes d'un projet achevé en 2020, d'un montant de 18 080 $US, y compris les coûts d’appui d’agence

Disponibilité des ressources

# L'état des contributions et des décaissements indique un solde restant de 385 240 783 US$ au 12 octobre 2021. Le solde total retourné par les agences bilatérales et d’exécution à la 88e réunion s'élève à 6 322 577 $US. Par conséquent, le niveau total des ressources disponibles pour les approbations lors de la 88e réunion est de 391 563 360 $US.

Observations du Secrétariat

# Le Secrétariat a rappelé aux agences bilatérales et d’exécution que les soldes des projets par décision et des projets achevés depuis un an ou plus doivent être restitués au Fonds Multilatéral dès que possible.

# Compte tenu du fait que le niveau de financement total des projets et activités soumis à la 88e réunion au 18 octobre 2021 s’élève à 81 490 200 $US, il y a suffisamment de ressources disponibles pour les approbations lors de cette réunion.

Recommandations

# Le Comité exécutif pourrait souhaiter :

## Prendre note:

- Du rapport sur les soldes et la disponibilité des ressources figurant dans le document UNEP/OzL.Pro/ExCom/88/4;

- Du fait que le montant net des fonds restitués à la 88e réunion par les agences d'exécution s'élève à 6 320 238 $US, comprenant 2 261 506 $US, plus les coûts d'appui d'agence de 168 607 $US pour le PNUD, 3 165 404 $US, plus les coûts d'appui d'agence de 241 892 $US pour le PNUE, 36 947 $US, plus les coûts d'appui d'agence de 2 678 $US pour l'ONUDI et 443 204 $US pour la Banque mondiale.

- Du fait que le PNUD détient des soldes de 25 773 $US, y compris les coûts d'appui d'agence, pour trois projets achevés plus de deux ans auparavant, et de 22 223 $US, y compris les coûts d'appui d'agence, pour trois projets financés au titre des contributions volontaires supplémentaires pour les activités de facilitation de la réduction progressive des HFC;

- Du fait que le PNUE détenait des soldes de 116 344 $US, y compris les coûts d'appui d'agence, pour deux projets achevés par décision du Comité exécutif;

- Du fait que le montant net des fonds restitués à la 88e réunion par le gouvernement de l'Australie est de 2 070 $US, plus des coûts d'appui d'agence de 269 $US;

## Prier:

### Les agences bilatérales et d’exécution de procéder au décaissement ou à l’annulation des fonds engagés et non engagés qui n'étaient pas nécessaires pour les projets achevés et les projets par décision du Comité exécutif, et de restituer les soldes associés à la 90e réunion;

### Le PNUD de procéder au décaissement ou à l'annulation des engagements pour les trois projets restants achevés depuis plus de deux ans, et de restituer les soldes à la 90e réunion;

### Le PNUD de restituer à la 90e réunion les soldes de trois projets achevés financés au titre des contributions volontaires supplémentaires;

### Le PNUE de restituer à la 90e réunion les soldes de deux projets achevés par décision du Comité exécutif, conformément à la décision 86/16 f) i);

### Le Trésorier d’assurer le suivi auprès du gouvernement australien pour la restitution, en espèces, de la somme de 2 339 $US mentionnée à l’alinéa a) v) ci-dessus.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2020(US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not-committed as per 88th meeting (US $) | Support cost on balances committed and not committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRU/PHA/82/INV/23 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 33,000 | 26,549 | 6,451 |  | 581 |  |  |  |
| COS/PHA/81/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Mar-20 | 40,000 | 38,883 | 1,117 |  | 78 |  |  |  |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 56,000 | 49,952 | 6,048 |  | 454 |  |  |  |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,459 | 5,398 |  | 378 |  |  |  |
| CUB/PHA/82/TAS/60 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 22,236 | 7,764 |  | 699 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,896,153 | 103,847 |  | 7,789 |  |  |  |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 530,037 | 186,363 |  | 13,977 |  |  |  |
| FIJ/PHA/73/INV/27 | HCFC phase-out management plan (stage I, second tranche) | Jun-17 | 37,900 | 17,955 | 19,945 |  | 1,795 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 55,584 | 4,266 |  | 384 |  |  |  |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 3,718 | 26,282 |  | 2,365 |  |  |  |
| GHA/PHA/81/INV/46 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 125,000 | 105,139 | 19,861 |  | 1,490 |  |  |  |
| GHA/PHA/81/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 60,000 | 49,389 | 10,611 |  | 743 |  |  |  |
| GHA/SEV/82/INS/47 | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | Dec-20 | 178,048 | 177,391 | 657 |  | 46 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | Jun-20 | 201,674 | 42,383 | 159,291 |  | 11,947 |  |  |  |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | Jun-20 | 512,190 | 244,358 | 267,832 |  | 20,087 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | Dec-19 | 477,734 | 477,682 | 52 |  | 4 |  |  |  |
| KYR/PHA/81/INV/40 | HCFC phase-out management plan (stage II, second tranche) | Dec-20 | 175,000 | 108,104 | 66,896 |  | 4,683 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,388,171 | 411,829 |  | 30,887 |  |  |  |
| MEX/REF/81/INV/187 | Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico | Nov-20 | 2,115,012 | 2,110,680 | 4,332 |  | 303 |  |  |  |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 29,919 | 10,081 |  | 706 |  |  |  |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 23,657 | 6,343 |  | 571 |  |  |  |
| SRL/SEV/82/INS/53 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | Dec-20 | 171,592 | 136,511 | 35,081 |  | 2,456 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 38,101 | 61,899 |  | 4,333 |  |  |  |
| URU/PHA/77/TAS/69 | HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring) | Dec-18 | 35,800 | 34,130 | 1,670 |  | 117 |  |  |  |
| URU/SEV/80/INS/70 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 193,024 | 192,729 | 295 |  | 21 |  |  |  |
| VEN/SEV/77/INS/135 | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | Mar-19 | 365,414 | 363,315 | 2,099 |  | 147 |  |  |  |
| ZIM/PHA/83/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 11,435 | 8,565 |  | 600 |  |  |  |
| TOTAL UNDP |  |  |  |  | 3,807,156 |  | 279,457 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| LAO/PHA/74/TAS/27 | HCFC phase-out management plan (stage I, second tranche) | Dec-20 | 97,875 | 86,875 |  | 11,000 | 1,430 | UNEP is working on financial closure of the project. | ExCom 90 |  |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 14,844 |  | 5,156 | 670 | Once project is financially completed | ExCom 89 |  |
| TOTAL UNEP |  |  |  |  |  | 16,157 | 2,100 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | Jun-20 | 1,637,610 | 1,524,521 | 113,089 |  | 7,917 | 3 | 90 |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 24,091 | 5,909 |  | 532 | 3 | 90 |  |
| NER/PHA/82/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 29,658 | 342 |  | 31 | 3 | 90 |  |
| PAK/PHA/76/TAS/95 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-20 | 190,000 | 180,077 | 9,923 |  | 695 | 3 | 90 |  |
| QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 39,629 | 372 |  | 26 | 3 | 90 |  |
| RWA/PHA/77/INV/27 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 55,000 | 54,664 | 336 |  | 30 | 3 | 90 |  |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,080,492 | 613,182 |  | 42,923 | 3 | 90 | 86/17(i)(i) |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Dec-20 | 1,300,000 | 903,494 | 396,506 |  | 27,755 | 3 | 90 | 83/33(c) and 85/17(c) |
| SIL/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 50,000 | 48,855 | 1,145 |  | 103 | 2 | 90 |  |
| SOA/PHA/67/TAS/04 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Dec-20 | 110,005 | 103,224 | 6,782 |  | 474 | 2 | 90 |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 3 | 90 |  |
| TOTAL UNIDO |  |  |  |  | 1,154,504 |  | 80,969 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| CPR/PHA/77/TAS/582 | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Dec-20 | 80,000 | 64,000 | 16,000 |  | 2,080 |  |  |  |
| TOTAL JAPAN |  |  |  |  | 16,000 |  | 2,080 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,364,430 | 126,179 |  | 8,832 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 126,179 |  | 8,832 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 182,206 | 32,350 |  | 4,007 |  |  | 86/16(f)(i) |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 50,589 | 71,170 |  | 8,817 |  |  | 86/16(f)(i) |
| TOTAL UNEP |  |  |  |  | 103,520 |  | 12,824 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COS/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 144,830 | 5,170 |  | 362 |  |  |
| JAM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 145,083 | 4,917 |  | 344 |  |  |
| TRI/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 139,318 | 10,682 |  | 748 |  |  |
| TOTAL UNDP |  |  |  | 20,769 |  | 1,454 |  |  |

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| ARM/PHA/84/TAS/23 | Verification report on the implementation of the HCFC phase-out management plan | 370 | 33 | 403 |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | 1,020,974 | 76,573 | 1,097,547 |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | 1,032,897 | 77,468 | 1,110,365 |
| COL/PHA/75/TAS/92 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | 5 | 0 | 5 |
| COS/REF/76/DEM/55 | Demonstration of the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A. | 697 | 49 | 746 |
| COS/SEV/75/INS/53 | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | 198 | 14 | 212 |
| CUB/SEV/75/INS/54 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 1 | 0 | 1 |
| DOM/REF/81/INV/63 | Conversion of a commercial refrigerator manufacturing line at Fábrica de Refrigeradores Comerciales, SRL (FARCO) from HFC-134a and R-404A to propane (R-290) as refrigerant | 24 | 2 | 26 |
| DRC/PHA/80/INV/45 | HCFC phase-out management plan (stage I, third tranche) | 476 | 43 | 519 |
| EGY/FOA/76/DEM/129 | Demonstration of low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users | 190,799 | 13,356 | 204,155 |
| EGY/PHA/74/PRP/126 | Preparation of a HCFC phase-out management plan (stage II) | 11,860 | 830 | 12,690 |
| ELS/PHA/77/INV/34 | HCFC phase-out management plan (stage I, third tranche) | 1,052 | 79 | 1,131 |
| IDS/PHA/71/INV/199 | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | 380 | 29 | 409 |
| IDS/SEV/75/INS/206 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 29 | 2 | 31 |
| IND/PHA/75/INV/463 | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | 48 | 4 | 52 |
| IND/SEV/72/INS/457 | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | 182 | 13 | 195 |
| MDV/PHA/69/INV/24 | HCFC phase-out management plan (second tranche) | 3 | 0 | 3 |
| NIR/PHA/75/INV/143 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing) | 1,511 | 113 | 1624 |
| Total completed projects |  | 2,261,506 | 168,607 | 2,430,113 |
| TOTAL UNDP |  | 2,261,506 | 168,607 | 2,430,113 |
| AFG/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 273 | 35 | 308 |
| AFG/SEV/80/INS/23 | Extension of institutional strengthening project (phase VIII: 1/2018-12/2019) | 5,754 | 0 | 5,754 |
| BEN/SEV/80/INS/35 | Renewal of institutional strengthening project (phase X: 1/2018-12/2019) | 2,663 | 0 | 2,663 |
| BKF/PHA/84/TAS/40 | Verification report on the implementation of the HCFC phase-out management plan | 710 | 92 | 802 |
| BZE/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 9,800 | 1,274 | 11,074 |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | 507 | 66 | 573 |
| CKI/SEV/77/INS/13 | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | 5,000 | 0 | 5,000 |
| ECU/PHA/76/TAS/64 | HCFC phase-out management plan (stage I, third tranche) | 14,590 | 1,897 | 16,487 |
| ECU/PHA/82/PRP/67 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 | 11,187 |
| ECU/PHA/82/TAS/69 | HCFC phase-out management plan (stage I, fourth tranche) | 1,235 | 161 | 1,396 |
| ECU/PHA/85/TAS/73 | HCFC phase-out management plan (stage I, fifth tranche) | 10,000 | 1,300 | 11,300 |
| ECU/PHA/86/TAS/74 | HCFC phase-out management plan (stage II, first tranche) | 24,000 | 3,120 | 27,120 |
| ECU/SEV/83/INS/71 | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) | 226,305 | 0 | 226,305 |
| ELS/PHA/65/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | 6,531 | 229 | 6,760 |
| ERI/PHA/82/TAS/17 | Verification report on the implementation of the HCFC phase-out management plan | 982 | 128 | 1,110 |
| FSM/SEV/77/INS/12 | Renewal of institutional strengthening project (phase VI: 1/2017-12/2018) | 969 | 0 | 969 |
| GAM/PHA/82/TAS/36 | Verification report on the implementation of the HCFC phase-out management plan | 1,096 | 142 | 1,238 |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | 22,921 | 2,980 | 25,901 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 10,677 | 854 | 11,531 |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | 2,611,540 | 208,923 | 2,820,463 |
| GUA/PHA/82/PRP/54 | Preparation of a HCFC phase-out management plan (stage II) | 1,828 | 238 | 2,066 |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | 20,109 | 2,614 | 22,723 |
| HON/PHA/82/PRP/46 | Preparation of a HCFC phase-out management plan (stage II) | 9,706 | 1,262 | 10,968 |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 4,734 | 582 | 5,316 |
| IRQ/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 6,886 | 895 | 7,781 |
| LAO/PHA/82/TAS/32 | Verification report on the implementation of the HCFC phase-out management plan | 5,780 | 751 | 6,531 |
| MAG/PHA/82/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 1,076 | 140 | 1,216 |
| MDV/SEV/81/INS/33 | Extension of the institutional strengthening project (phase X: 12/2018-11/2020) | 10,000 | 0 | 10,000 |
| MLW/PHA/82/TAS/44 | Verification report on the implementation of the HCFC phase-out management plan | 1,547 | 201 | 1,748 |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | 18,617 | 0 | 18,617 |
| MON/PHA/82/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 1,967 | 256 | 2,223 |
| NEP/PHA/82/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 4,744 | 617 | 5,361 |
| NIC/PHA/74/TAS/31 | HCFC phase-out management plan (stage I, second tranche) | 3,072 | 399 | 3,471 |
| NIC/PHA/83/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | 4,938 | 0 | 4,938 |
| SAM/PHA/82/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 2,519 | 327 | 2,846 |
| SOI/PHA/82/TAS/15 | Verification report on the implementation of the HCFC phase-out management plan | 7,926 | 1,030 | 8,956 |
| STV/PHA/77/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 14,738 | 1,916 | 16,654 |
| SYR/PHA/83/PRP/105 | Preparation of a HCFC phase-out management plan (stage II) | 17,375 | 2,259 | 19,634 |
| TON/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,589 | 727 | 6,316 |
| TTR/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,623 | 731 | 6,354 |
| UGA/PHA/77/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 3,500 | 455 | 3,955 |
| UGA/PHA/82/TAS/25 | Verification report on the implementation of the HCFC phase-out management plan | 380 | 49 | 429 |
| URT/PHA/82/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 485 | 63 | 548 |
| ZAM/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 529 | 69 | 598 |
| Total completed projects |  | 3,128,821 | 239,331 | 3,368,152 |
| MON/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 2,134 | 149 | 2,283 |
| TTR/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 25,000 | 1,750 | 26,750 |
| ZIM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 9,449 | 661 | 10,110 |
| Total “additional voluntary contributions” projects |  | 36,583 | 2,561 | 39,143 |
| TOTAL UNEP |  | 3,165,404 | 241,892 | 3,407,296 |
| ARG/PHA/79/TAS/181 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 1,298 | 91 | 1,389 |
| BOL/PHA/82/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 681 | 51 | 732 |
| EGY/SEV/81/INS/138 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 1,253 | 88 | 1,341 |
| GAB/PHA/62/INV/27 | HCFC phase-out management plan (stage I, first tranche) | 42 | 4 | 46 |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | 3,212 | 225 | 3,437 |
| GUA/PHA/84/TAS/56 | Verification report on the implementation of the HCFC phase-out management plan | 3,403 | 306 | 3,709 |
| HON/PHA/84/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 285 | 26 | 311 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| SAU/PHA/68/INV/19 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 215 | 15 | 230 |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | 521 | 39 | 560 |
| SEN/PHA/77/INV/36 | HCFC phase-out management plan (stage I, second tranche) | 1,988 | 149 | 2,137 |
| SOM/PHA/77/TAS/13 | HCFC phase-out management plan (stage I, second tranche) (additional security) | 8,172 | 572 | 8,744 |
| TKM/PHA/76/INV/12 | HCFC phase-out management plan (stage I, third tranche) | 91 | 7 | 98 |
| UGA/PHA/82/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| Total completed projects |  | 27,841 | 2,040 | 29,881 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| Total “by decision” projects |  | 6,628 | 464 | 7,092 |
| ARM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 361 | 26 | 387 |
| LEB/REF/80/PRP/01 | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 2,106 | 147 | 2,253 |
| TUN/SEV/80/TAS/02 | Enabling activities for HFC phase-down | 10 | 1 | 11 |
| Total “additional voluntary contributions” projects |  | 2,478 | 174 | 2,652 |
| TOTAL UNIDO |  | 36,947 | 2,678 | 39,625 |
| GLO/SEV/84/TAS/351 | Core unit budget (2020) | 0 | 443,204 | 443,204 |
| TOTAL WORLD BANK |  |  | 443,204 | 443,204 |
| IDS/PHA/64/TAS/196 | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | 2,070 | 269 | 2,339 |
| TOTAL AUSTRALIA |  | 2,070 | 269 | 2,339 |

Les réunions en ligne et un processus d'approbation intersessions se tiendront en novembre et décembre 2021 en raison du coronavirus (COVID-19).

Les données sont présentées selon le modèle d’établissement de rapport élaboré dans la foulée de la décision 31/2.

UNEP/OzL.Pro/ExCom/88/3

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred.