| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/16 25 October 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-eighth Meeting

Montreal, 15-19 November 2021

PROGRESS REPORT OF UNIDO as at 31 december 2020

# This document presents the progress report of UNIDO as at 31 December 2020.

Introduction

# The progress report of UNIDO includes the status of implementation of projects, including 35 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2020, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in mt CO2-eq.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2020 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down. It provides a summary on the status of implementation of HFC phase-down projects funded under the voluntary contributions.

## Recommendation.

# The document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2020 and cumulative

# Implementation of projects and activities by UNIDO for 2020 and cumulative since 1993 up to 31 December 2020, is summarized as follows:

## Phase-out: In 2020, 213.2 ODP tonnes of consumption of controlled substances were phased out and an additional 662.4 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1993, 63,143 ODP tonnes and 211,531 mt CO2-eq of consumption of controlled substances and 17,381 ODP tonnes of production of controlled substances had been phased out, of an expected total of 82,604 ODP tonnes and 211,531 mt CO2-eq from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2020, US $20.65 million was disbursed and US $23.16 million was planned for disbursement based on the 2019 progress report, representing a rate of disbursement of 89 per cent of that planned. Cumulatively, US $761.33 million had been disbursed out of the total US $853.87 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 89 per cent. In 2020, US $15.74 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.20/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $2.93/kg. The average cost-effectiveness of investment projects per ODP tonne was US $7.36/kg for completed projects and US $45.75/kg for ongoing projects;

## Number of projects completed: In 2020, 48 projects were completed. Since 1993, 1,604 projects of the 1,851 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 87 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2020 were completed on average 67 months after their approval. Since 1993, the average time for completion of investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2020 were completed on average 40 months after their approval. Since 1993, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 546 project preparation activities approved by the end of 2020, 488 have been completed, leaving 58 ongoing activities. In 2020, 13 preparation activities have been completed;

## Implementation delays: A total of 247 projects were under implementation at the end of 2020, experiencing, on average, a delay of 23 months. Thirty-five of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2020, one MYA for ODS phase-out, one MYA for MB production phase-out, one for control and phase-out of HFC-23 emissions and 79 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1993, 175 MYAs have been approved and 93 MYAs have been completed, representing a completion rate of 53 per cent.

Project implementation progress in 2020

# Further to the review process, a number of issues were discussed and satisfactorily addressed, except for issues on 35 projects classified as projects with implementation delays (including 33 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and two investment projects). Annex I to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendation requesting the submission of a report to the 90th meeting.

# In addition, a number of issues were identified regarding projects, tranches of MYAs, and preparation of HPMPs. These issues are also presented in Annex I to the present document. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Bahrain, Brazil, Cameroon, Chile, China (extruded polystyrene foam sector plan and room air-conditioning sector plan), Egypt, Ethiopia, Kuwait, Niger (the), North Macedonia, Oman, Pakistan, Qatar, Senegal, and the Sudan, and reports on projects with specific reporting requirements associated with Libya (HPMP), and Saudi Arabia (HPMP), and China (MB production phase-out plan), have been submitted to the 88th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of these documents. The issues relating to the HPMPs for Algeria, Argentina, Islamic Republic of Iran, Jordan, South Africa and Suriname that were due at the 88th meeting but were not submitted, and for Mexico and Venezuela (Bolivarian Republic of) that were submitted to the 88th meeting but subsequently withdrawn during the project review process, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in Annex I to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 170 ongoing projects, excluding IS and project preparation, 81 projects have revised planned dates of completion since the 2019 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for the Syrian Arab Republic had not been submitted for the last two years; the main reason is a large balance still available due to slow progress in implementation; however, UNIDO is planning to submit the renewal request in 2022.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of a number of HPMPs to beyond 31 December 2022; those that have not been submitted as part of the tranche requests are addressed in the document on reports on projects with specific reporting requirements. In addition, UNIDO has requested the extension of the duration of one chiller project and one project for enabling activities for the phase-down of HFCs, as shown in Table 1.

Table 1. Projects for which an extension of the completion dates has been requested

| Country/Project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Global chiller project (Argentina) GLO/REF/80/DEM/344 | Global chiller project (Argentina) | 13 | Additional time needed for procurement and installation of equipment and recovery of CFCs from the existing chillers | Dec-21 | Dec-22 |
| Jordan JOR/SEV/82/TAS/104 | Enabling activities for HFC phase-down | 42 | Due to COVID-19 restrictions, additional time needed for completing workshops for awareness on HFC phase-down, energy efficiency improvement, monitoring and controlling HFCs | Dec-21 | Jun-22 |

Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2020, the Executive Committee had approved 35 HFC-related projects under the additional voluntary contributions, amounting to US $8,085,163 (excluding agency support costs). A summary of the status of these projects is presented in Table 2.

# Table 2. Status of approved HFC-related projects as of the end of 2020

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 1 | 33% | 3,912,736 | 2,116,176 | 1,796,560 | 54 |
| Project preparation | 4 | 4 | 100% | 119,755 | 101,389 | 18,366 | 85 |
| Technical assistance - Enabling activities | 28 | 8 | 29% | 4,052,672 | 2,860,759 | 1,191,913 | 71 |
| Total | 35 | 13 | 37% | 8,085,163 | 5,078,324 | 3,006,839 | 63 |

* Excludes agency support costs.

** 112.5 mt (245,860 mt CO2-eq) of 265.1 mt (508,586 mt CO2-eq.) of HFCs had been phased out.

# As of the end of 2020, of the 35 projects approved, 13 projects had been completed including one investment project, four preparation activities and eight enabling activities, leaving 22 ongoing. Extension of the completion dates of the 20 ongoing enabling activities was approved; these activities are at various stages of implementation.

# In line with decision 82/11(b), UNIDO has requested further extension of the duration of three projects for enabling activities as shown in Table 3.

Table 3. Projects for which an extension of the completion dates has been requested

| Country/Project code | Project title | Disburse-ment (%) | Status/issues | Revised completion date | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Chile CHI/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 22 | Due to COVID-19 restrictions, additional time needed for completing activities relating to training on policies for HFC controls, energy efficiency and service sector for safe adoption of flammable refrigerants | Dec-21 | Jun-22 |
| Morocco MOR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 9 | Due to COVID-19 restrictions, additional time needed for completing HFC consumption survey and providing support for ratification of Kigali Amendment | Jan-22 | Dec-22 |
| Uruguay URU/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 87 | Due to COVID-19 restrictions, additional time needed for completing the training programme for technicians on handling of hydrocarbon (HC)-based refrigerants, and end-users activities to reduce HFC consumption, and to promote reclamation of refrigerants | Dec-21 | Jun-22 |

# Ongoing investment projects include two projects in the refrigeration sector in Argentina and Mexico, which were approved at the 81st meeting; these projects will be completed in 2021 and 2022, respectively. Further to the review process, these projects are classified as projects with implementation delays and are included in Annex I to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 90th meeting.

# Of the total cumulative funding approved of US $8,085,163, US $5,078,324 had been disbursed representing a disbursement rate of 63 per cent.

# Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2020 contained in document UNEP/OzL.Pro/ExCom/88/16;

## To approve the extension of the completion dates of the projects listed below to allow for completion of the remaining ongoing activities as reflected in Table 1 of document UNEP/OzL.Pro/ExCom/88/16:

### Enabling activities for HFC phase-down for Jordan (JOR/SEV/82/TAS/104) to 30 June 2022;

### Global chiller replacement project for Argentina (GLO/REF/80/DEM/344) to 31 December 2022;

## To approve the extension of the completion dates of the projects listed below to allow for completion of the remaining ongoing activities as reflected in Table 3 of document UNEP/OzL.Pro/ExCom/88/16:

### Enabling activities for HFC phase-down for Chile (CHI/SEV/80/TAS/02+) to 30 June 2022;

### Enabling activities for HFC phase-down for Morocco (MOR/SEV/81/TAS/01+) to 31 December 2022;

### Enabling activities for HFC phase-down for Uruguay (URU/SEV/80/TAS/01+) to 30 June 2022; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document.

### .

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code* | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | 98 | 1) 12 months delays 2) Implementation delays due to political situation and lack of national ozone unit (NOU) staff | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on the implementation progress |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 0 | 1) 12 and 18 months delays 2) Implementation delays due to political situation and lack of NOU staff; disbursement is nil | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on the implementation progress and on disbursement level |
| Afghanistan AFG/PHA/82/PRP/25 | Preparation of a HCFC phase-out management plan (stage II) | 92 | Implementation delays due to political situation and lack of NOU staff | To request UNIDO to provide a status report to the 90th meeting on the implementation progress |
| Afghanistan AFG/PHA/85/INV/28 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Implementation delays due to political situation and lack of NOU staff | To request UNIDO to provide a status report to the 90th meeting on the implementation progress |
| Afghanistan AFG/PHA/85/INV/30 | HCFC phase-out management plan (stage II, first tranche) | 0 | 1) 12 months delays 2) Implementation delays due to political situation and lack of NOU staff; disbursement is nil | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on the implementation progress and on disbursement level |
| Albania ALB/PHA/85/INV/41 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/76 | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | 64 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/77 | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | 45 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Argentina ARG/PHA/79/INV/180 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 85 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Argentina ARG/PHA/80/INV/184 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 34 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Argentina ARG/PHA/80/TAS/185 | HCFC phase-out management plan (stage II, first tranche) (management and coordination) | 87 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/TAS/191 | HCFC phase-out management plan (stage II, second tranche) (monitoring and reporting of HCFC-22 production) | 0 | Delay in verification report due to COVID-19 travel restrictions; disbursement is nil | To request UNIDO to provide a status report to the 90th meeting on the completion of verification report of HCFC-22 production and on disbursement level |
| Argentina ARG/REF/81/INV/01+ | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen | 58 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Global chiller project (Argentina) GLO/REF/80/DEM/344 | Global chiller project (Argentina) | 13 | Additional time needed for procurement and installation of equipment and recovery of CFCs from the existing chillers | To request UNIDO to provide a status report to the 90th meeting on procurement and installation of chillers and recovery of CFCs from the existing chillers |
| Botswana BOT/PHA/75/INV/18 | HCFC phase-out management plan (stage I, first tranche) | 90 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Botswana BOT/PHA/82/INV/21 | HCFC phase-out management plan (stage I, second tranche) | 0 | 18 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Congo (the) PRC/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | 89 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/228 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 61 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/239 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 2 | 12 months delays; low level of disbursement | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/240 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 0 | 12 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iraq IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | 89 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iraq IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 19 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Iraq IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 89 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Jordan JOR/PHA/77/INV/100 | HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector) | 64 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Jordan JOR/PHA/77/INV/101 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 48 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Jordan JOR/PHA/84/INV/106 | HCFC phase-out management plan (stage II, second tranche) (polyurethane spray foam sector) | 0 | Delay due to COVID-19 restrictions for finalising working agreements with beneficiaries; disbursement is nil | To request UNIDO to provide a status report to the 90th meeting on implementation progress and disbursement level |
| Jordan JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | 2 | Delay due to COVID-19 restrictions for conducting training programmes and meetings relating to the project; low level of disbursement | To request UNIDO to provide a status report to the 90th meeting on implementation progress and disbursement level |
| Libya LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | 71 | 1) 12 months delays 2) Implementation slow due to political situation in the country | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on implementation progress |
| Libya LIB/PHA/75/INV/37 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 54 | 1) 12 months delays 2) Implementation slow due to political situation in the country | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on implementation progress |
| Libya LIB/PHA/82/INV/42 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 12 | 1) 12 months delays 2) Implementation slow due to political situation in the country | 1) To request UNIDO to report to the 90th meeting on this project with implementation delays 2) To request UNIDO to provide a status report to the 90th meeting on implementation progress |
| Libya LIB/FOA/82/PRP/41 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 6 | Implementation slow due to political situation in the country; low level of disbursement | To request UNIDO to provide a status report to the 90th meeting on finalisation of stage II of the HPMP and disbursement level |
| Libya LIB/FOA/82/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 0 | Implementation slow due to political situation in the country; disbursement is nil | To request UNIDO to provide a status report to the 90th meeting on finalisation of stage II of the HPMP and disbursement level |
| Madagascar MAG/PHA/76/INV/28 | HCFC phase-out management plan (stage I, third tranche) | 96 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Mexico MEX/PHA/77/INV/183 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 97 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Mexico MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 1 | 12 months delays; low level of disbursement | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Montenegro MOG/PHA/85/INV/16 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Mozambique MOZ/PHA/83/INV/31 | HCFC phase-out management plan (stage I, third and fourth tranches) | 0 | 18 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| MYA/PHA/80/INV/19 | HCFC phase-out management plan (stage I, second tranche) | 90 | Implementation delays due to political situation and discontinuation of UN communication with the Government | To request UNIDO to provide a status report to the 90th meeting on implementation progress with an update on resumption of activities |
| MYA/PHA/83/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | 0 | Implementation delays due to political situation and discontinuation of UN communication with the Government; disbursement is nil | To request UNIDO to provide a status report to the 90th meeting on finalisation of stage II of the HPMP |
| South Africa SOA/PHA/71/INV/06 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, customs training and monitoring) | 94 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| South Africa SOA/PHA/83/TAS/13 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 0 | 18 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Syrian Arab Republic SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | 69 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Turkmenistan TKM/PHA/86/INV/17 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| United Republic of Tanzania (the) URT/PHA/76/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 66 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Venezuela (Bolivarian Republic of) VEN/PHA/76/INV/134 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in refrigeration and air-conditioning manufacturing sector) | 69 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Venezuela (Bolivarian Republic of) VEN/PHA/76/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 64 | 12 months delays | To request UNIDO to report to the 90th meeting on this project with implementation delays |
| Zambia ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 0 | 12 and 18 months delays; disbursement is nil | To request UNIDO to report to the 90th meeting on this project with implementation delays |

* Codes ending with “+” are from the additional contributions.

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNIDO AS AT 31 DECEMBER 2020

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2020, the Executive Committee had approved US $966.76 million, consisting of US $853.87 million for the implementation of investment and non-investment projects, and US $112.89 million for agency support costs, as shown in Table 1. In 2020, 58 new projects and activities were approved. This level of funding is expected to result in the phase-out of 82,604 ODP tonnes of consumption and production of controlled substances.

# Table 1: Approved funding by sector for UNIDO as at 31 December 2020

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,413,701 |
| Destruction | 3,805,540 |
| Foam | 89,105,490 |
| Halon | 1,780,369 |
| Fumigants | 78,028,741 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 353,091,265 |
| Process agent | 6,337,359 |
| Production | 51,128,201 |
| Refrigeration | 182,191,775 |
| Several | 19,287,372 |
| Solvents | 23,247,443 |
| Sub-total | 853,873,942 |
| Agency support costs | 112,890,657 |
| Total | 966,764,599 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 43 | 42 | 98 | 23,417,099 | 22,299,665 | 1,117,433 | 95 |
| Institutional strengthening (IS) | 92 | 73 | 79 | 14,689,423 | 12,110,188 | 2,579,235 | 82 |
| Investment | 937 | 795 | 85 | 766,940,563 | 684,379,507 | 82,561,056 | 89 |
| Project preparation | 546 | 488 | 89 | 22,866,295 | 21,261,834 | 1,604,460 | 93 |
| Technical assistance | 199 | 172 | 86 | 24,041,358 | 19,359,997 | 4,681,361 | 81 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,535 | 0 | 100 |
| Total | 1,851 | 1,604 | 87 | 853,873,942 | 761,330,396 | 92,543,546 | 89 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and the end of 2007, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | 0 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,038 | 0 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,291 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,752 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,255 | 0 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,041 | 1 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,807 | 1 | 100 |
| 2006 | 44 | 44 | 100 | 20,760,993 | 20,675,405 | 85,588 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,741 | -1 | 100 |
| 2008 | 77 | 76 | 99 | 33,405,264 | 33,376,488 | 28,776 | 100 |
| 2009 | 70 | 68 | 97 | 15,409,470 | 14,695,887 | 713,583 | 95 |
| 2010 | 69 | 66 | 96 | 46,082,170 | 45,103,864 | 978,306 | 98 |
| 2011 | 71 | 70 | 99 | 76,615,828 | 72,899,639 | 3,716,189 | 95 |
| 2012 | 52 | 43 | 83 | 32,682,508 | 30,337,834 | 2,344,673 | 93 |
| 2013 | 37 | 35 | 95 | 31,118,774 | 30,234,460 | 884,314 | 97 |
| 2014 | 55 | 43 | 78 | 27,880,007 | 25,587,498 | 2,292,509 | 92 |
| 2015 | 84 | 68 | 81 | 37,319,256 | 24,033,752 | 13,285,504 | 64 |
| 2016 | 58 | 34 | 59 | 35,715,549 | 20,505,331 | 15,210,218 | 57 |
| 2017 | 28 | 11 | 39 | 16,458,925 | 11,533,231 | 4,925,694 | 70 |
| 2018 | 62 | 22 | 35 | 27,168,885 | 9,704,702 | 17,464,183 | 36 |
| 2019 | 66 | 4 | 6 | 19,508,378 | 1,598,283 | 17,910,095 | 8 |
| 2020 | 58 | 0 | 0 | 15,743,901 | 3,039,987 | 12,703,914 | 19 |
| Total | 1,851 | 1,604 | 87 | 853,873,942 | 761,330,396 | 92,543,546 | 89 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Table 4 presents project implementation by country for 2020.

Table 4. Summary of project implementation by UNIDO for 2020

| Country | Phased out in 2020 (ODP tonnes)* | Percentage of planned phase-out achieved in 2020 | Estimated funds disbursed in 2020 (US$) | Funds disbursed in 2020 (US$) | Percentage of funds disbursed over estimation in 2020 | Percentage of planned projects completed in 2020 |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.2 |  | 50,000 | 51,665 | 103 | 0 |
| Albania | 0.0 |  | 32,500 | 35,797 | 110 | 100 |
| Algeria | 0.0 |  | 110,000 | 56,864 | 52 | 0 |
| Argentina | 4.7 | 100 | 581,301 | 709,564 | 122 | 75 |
| Armenia | 0.0 |  | 77,080 | 95,697 | 124 |  |
| Bahamas (the) | 0.0 |  | 15,244 | 14,880 | 98 |  |
| Bahrain | 0.0 |  | 15,002 | 6,823 | 45 |  |
| Benin | 0.0 |  | 10,009 | 0 | 0 | 100 |
| Bolivia (Plurinational State of) | 0.5 |  | 28,001 | 29,133 | 104 | 0 |
| Bosnia and Herzegovina | 0.0 |  | 99,500 | 95,096 | 96 | 0 |
| Botswana | 0.0 |  | 172,800 | 66,557 | 39 |  |
| Brazil | 0.0 |  | 1,106,216 | 777,431 | 70 | 0 |
| Burkina Faso | 0.0 |  | 69,991 | 55,967 | 80 |  |
| Burundi | 0.0 |  | 26,000 | 13,639 | 52 |  |
| Cameroon | 0.1 |  | 29,001 | 34,355 | 118 |  |
| Chad | 0.0 |  | 5,000 | 0 | 0 |  |
| Chile | 1.7 |  | 301,400 | 29,647 | 10 |  |
| China | 26.1 | 0 | 7,081,262 | 7,975,477 | 113 | 17 |
| Congo (the) | 0.0 | 0 | 12,000 | 21,165 | 176 | 0 |
| Cote D'Ivoire | 0.1 |  | 75,000 | 33,810 | 45 |  |
| Ecuador | 7.7 |  | 192,983 | 198,098 | 103 | 100 |
| Egypt | 21.1 |  | 1,365,534 | 1,093,458 | 80 |  |
| Equatorial Guinea | 0.0 |  | 43,000 | 51,301 | 119 |  |
| Eritrea | 0.0 |  | 3,350 | 89 | 3 |  |
| Ethiopia | 0.0 |  | 73,000 | 0 | 0 |  |
| Gabon | 0.0 |  | 84,000 | 84,212 | 100 |  |
| Gambia (the) | 0.0 |  | 7,344 | 8,693 | 118 | 0 |
| Grenada | 0.0 |  | 1,919 | 1,919 | 100 |  |
| Guatemala | 0.8 |  | 34,500 | 51,589 | 150 | 100 |
| Guinea-Bissau | 0.0 |  | 14,000 | 2,550 | 18 | 100 |
| Honduras | 0.0 |  | 45,300 | 80,142 | 177 | 100 |
| Iran (Islamic Republic of) | 0.1 |  | 209,259 | 33,838 | 16 |  |
| Iraq | 0.0 |  | 638,895 | 3,124 | 0 | 0 |
| Jordan | 118.7 | 0 | 958,785 | 1,208,360 | 126 | 100 |
| Democratic People’s Republic of Korea (the) | 0.0 |  | 4 | 21,485 | 537117 |  |
| Kuwait | 0.0 |  | 3,310,000 | 3,034,632 | 92 |  |
| Lebanon | 0.0 |  | 24 | 25 | 104 | 100 |
| Liberia | 0.0 |  | 2,000 | 0 | 0 |  |
| Libya | 0.0 |  | 171,004 | 92,179 | 54 | 0 |
| Madagascar | 0.0 |  | 80,302 | 74,783 | 93 |  |
| Malawi | 0.0 |  | 9,410 | 9,384 | 100 | 100 |
| Mexico | 0.0 |  | 505,774 | 224,177 | 44 | 25 |
| Montenegro | 0.0 |  | 30,001 | 53,352 | 178 | 100 |
| Morocco | 0.0 |  | 122,000 | 85,655 | 70 | 100 |
| Mozambique | 0.0 |  | 19,001 | 53,579 | 282 |  |
| Myanmar | 0.0 |  | 3,882 | 2,036 | 52 |  |
| Nicaragua | 0.8 |  | 54,400 | 52,926 | 97 |  |
| Niger (the) | 0.0 |  | 67,000 | 3,747 | 6 | 100 |
| Nigeria | 0.2 |  | 140,969 | 52,050 | 37 |  |
| North Macedonia | 0.1 |  | 75,001 | 115,312 | 154 |  |
| Oman | 0.0 |  | 85,001 | 59,450 | 70 | 0 |
| Pakistan | 0.0 |  | 1,535,000 | 189,718 | 12 |  |
| Philippines (the) | 0.0 |  | 110,000 | 131,619 | 120 |  |
| Qatar | 1.6 | 100 | 7,002 | 29,104 | 416 | 100 |
| Rwanda | 0.2 | 100 | 49,081 | 52,681 | 107 | 100 |
| Saint Lucia | 0.0 |  | 20,342 | 19,892 | 98 |  |
| Saudi Arabia | 19.0 |  | 508,115 | 786,247 | 155 | 67 |
| Senegal | 0.0 |  | 44,000 | 53,334 | 121 | 100 |
| Serbia | 0.0 |  | 124,602 | 66,301 | 53 | 50 |
| Sierra Leone | 0.0 |  | 6,510 | 5,165 | 79 | 100 |
| Somalia | 0.0 |  | 44,000 | 20,475 | 47 | 0 |
| South Africa | 0.0 |  | 163,300 | 119,458 | 73 | 25 |
| Sudan (the) | 0.0 |  | 693,155 | 267,925 | 39 |  |
| Suriname | 0.1 |  | 4,000 | 0 | 0 |  |
| Syrian Arab Republic | 0.0 |  | 36,001 | 622,522 | 1729 |  |
| United Republic of Tanzania (the) | 0.0 |  | 33,500 | 29,225 | 87 |  |
| Togo | 3.6 |  | 111,077 | 125,590 | 113 |  |
| Tunisia | 5.8 |  | 533,300 | 294,083 | 55 | 0% |
| Turkey | 0.0 |  | 784,020 | 814,128 | 104 | 100% |
| Turkmenistan | 0.0 |  | 44,000 | 65,628 | 149 | 100% |
| Uganda | 0.0 |  | 3,430 | 4,464 | 130 |  |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 11,201 | 11,202 | 100 |  |
| Zambia | 0.0 |  | 12,000 | 0 | 0 |  |
| Global | 0.0 |  | 35,447 | 82,861 | 234 | 100 |
| Region: ASP | 0.0 |  | 3,300 | 4,347 | 132 |  |
| Grand Total | 213.2 | 2 | 23,161,332 | 20,651,680 | 89 | 51 |

* 118.7 mt (211,531 mt CO2-eq.) phased out in 2020 for HFC-related projects.

# Table 5 presents a summary of HFC-related projects approved under regular contributions.

Table 5. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 | 1 | 50 | 2,120,668 | 1,524,521 | 596,147 | 72 |
| Project preparation | 3 | 2 | 67 | 159,816 | 129,510 | 30,306 | 81 |
| Technical assistance - Enabling activities | 3 | 0 | 0 | 400,000 | 110,439 | 289,561 | 28 |
| Total | 8 | 3 | 38 | 2,680,484 | 1,764,470 | 916,014 | 66 |

* Excludes agency support costs.

** 118.7 mt (211,531 mt CO2-eq.) was approved and phased out for investment projects.

# There are currently eight HFC-related projects (including two investment projects, three project preparation and three enabling activities). Of the eight projects, one investment and two preparation projects have been completed, leaving five ongoing. Extension of the completion dates of three enabling activities was approved; these activities are at various stages of implementation.

# The ongoing HFC investment project related to the control and phase-out of HFC-23 in Mexico approved at the 86th meeting and will be completed in October 2022.

# Of the total cumulative funding approved of US $2,680,484 (excluding agency support costs), US $1,764,470 had been disbursed, representing a disbursement rate of 66 per cent.

# Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2020, the Executive Committee had approved 35 HFC-related projects under the additional voluntary contributions amounting to US $8,085,163 (excluding agency support costs). A summary of the status of these projects is presented in Table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2020

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 1 | 33% | 3,912,736 | 2,116,176 | 1,796,560 | 54 |
| Project preparation | 4 | 4 | 100% | 119,755 | 101,389 | 18,366 | 85 |
| Technical assistance - Enabling activities | 28 | 8 | 29% | 4,052,672 | 2,860,759 | 1,191,913 | 71 |
| Total | 35 | 13 | 37% | 8,085,163 | 5,078,324 | 3,006,839 | 63 |

* Excludes agency support costs.

** 112.5 mt (245,860 mt CO2-eq) of 265.1 mt (508,586 mt CO2-eq.) of HFCs had been phased out.

# As of the end of 2020, of the 35 projects approved, 13 projects had been completed including one investment project, four preparation activities and eight enabling activities, leaving 22 ongoing. Extension of the completion dates of the 20 ongoing enabling activities was approved; these activities are at various stages of implementation.

# Ongoing investment projects include two projects in the refrigeration sector in Argentina and Mexico, which were approved at the 81st meeting; these projects will be completed in 2021 and 2022, respectively.

# Of the total cumulative funding approved of US $8,085,163, US $5,078,324 had been disbursed representing a disbursement rate of 63 per cent.

Online meetings and an intersessional approval process will be held in November and December 2021 due to coronavirus disease (COVID-19)

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in mt CO2-eq. is included in the progress reports submitted to the 88th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2020. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/88/12).

UNIDO became an implementing agency in 1993.

Including 118.7 mt (211,531 mt CO2-eq.) phased out in 2020 for HFC-related projects.

Including 118.7 mt of HFC investment projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61) (as demonstration projects, project preparation, and institutional strengthening (IS) are not subject to those procedures).

UNEP/OzL.Pro/ExCom/88/38

UNEP/OzL.Pro/ExCom/88/39

UNEP/OzL.Pro/ExCom/88/41

UNEP/OzL.Pro/ExCom/88/42

UNEP/OzL.Pro/ExCom/88/43

UNEP/OzL.Pro/ExCom/88/47

UNEP/OzL.Pro/ExCom/88/48

UNEP/OzL.Pro/ExCom/88/52

UNEP/OzL.Pro/ExCom/88/55

UNEP/OzL.Pro/ExCom/88/57

UNEP/OzL.Pro/ExCom/88/58

UNEP/OzL.Pro/ExCom/88/59

UNEP/OzL.Pro/ExCom/88/60

UNEP/OzL.Pro/ExCom/88/62

UNEP/OzL.Pro/ExCom/88/64

UNEP/OzL.Pro/ExCom/88/18

UNEP/OzL.Pro/ExCom/88/18/Add.1

UNEP/OzL.Pro/ExCom/88/21

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

UNEP/OzL.Pro/ExCom/88/18

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.