| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/13 7 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 7(a)(iii) of the provisional agenda

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2024

Introduction

# This document presents the progress report of UNDP as at 31 December 2024.

# The progress report of UNDP includes the status of implementation of projects, including HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2024, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2024 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2024 and cumulative since 1991

# As of 31 December 2024, the Executive Committee had approved US $1.1 billion in projects for UNDP, consisting of US $967.52 million for the implementation of investment and non-investment projects and US $134.12 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNDP as at 31 December 2024

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 26,054,837 |
| Destruction | 4,436,037 |
| Energy efficiency | 2,362,019 |
| Foam | 174,543,644 |
| Halon | 4,996,973 |
| HFC phase-down plan | 16,001,127 |
| Fumigants | 20,081,241 |
| Phase-out plan | 427,990,351 |
| Process agent | 1,286,923 |
| Production | 1,060,066 |
| Refrigeration | 142,922,668 |
| Several | 81,663,722 |
| Solvents | 63,699,997 |
| Sterilant | 417,628 |
| Sub-total | 967,517,233 |
| Agency support costs | 134,117,165 |
| Total | 1,101,634,398 |

# In 2024, 75 new projects and activities were approved. This level of funding is expected to result in the phase-out of 70,528 ODP tonnes of consumption of ODS and 2,605 mt (5,549,026 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2024.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2024. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2024

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 22 | 22 | 100 | 1,628,797 | 1,628,797 | 0 | 100 |
| Demonstration | 43 | 42 | 98 | 21,868,769 | 21,718,833 | 149,936 | 99 |
| Institutional strengthening (IS) | 293 | 270 | 92 | 69,833,208 | 59,844,685 | 9,988,523 | 86 |
| Investment | 1,437 | 1,332 | 93 | 791,325,150 | 728,349,394 | 62,975,756 | 92 |
| Project preparation | 619 | 581 | 94 | 28,922,871 | 26,021,537 | 2,901,334 | 90 |
| Technical assistance | 360 | 345 | 96 | 52,347,949 | 49,529,425 | 2,818,524 | 95 |
| Training | 28 | 28 | 100 | 1,590,489 | 1,590,489 | 0 | 100 |
| Total | 2,802 | 2,620 | 94 | 967,517,233 | 888,683,160 | 78,834,073 | 92 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Implementation of projects and activities by UNDP for 2024 and cumulative since 1991 up to 31 December 2024 is summarized as follows:

## Phase-out: In 2024, 401.5 ODP tonnes of consumption of ODS were phased out and an additional 188.1 ODP tonnes of consumption of ODS and 949.2 mt (2,571,839 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 69,342 ODP tonnes had been phased out, of an expected total of 70,528 ODP tonnes of consumption of ODS and 648.4 mt (827,395 CO2-eq tonnes) had been phased out, of an expected total of 2,605 mt (5,549,026 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2024, US $18.75 million was disbursed and US $19.67 million was planned for disbursement based on the 2023 progress report, representing a rate of disbursement of 95 per cent of that planned. Cumulatively, US $888.68 million had been disbursed out of the total US $967.52 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 92 per cent. In 2024, US $32.67 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.50/kg. The average cost-effectiveness of investment projects per ODP tonne was US $11.01/kg for completed projects and US $20.81/kg for ongoing projects;

## Number of projects completed: In 2024, 66 projects were completed. Since 1991, 2,620 projects of the 2,802 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 94 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2024 were completed on average 43 months after their approval. Since 1991, the average time for completion of investment projects has been 34 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2024 were completed on average 27 months after their approval. Since 1991, the average time for completion of non-investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 619 project preparation activities approved by the end of 2024, 581 have been completed, leaving 38 ongoing activities. In 2024, 25 projects preparation activities were completed;

## Implementation delays: A total of 182 projects were under implementation at the end of 2024, experiencing, on average, a delay of four months. Fifteen of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2024, 44 MYAs for HCFC phase-out management plans (HPMPs) and 21 Kigali HFC implementation plans (KIPs) were under implementation. Since 1991, 186 MYAs have been approved and 121 MYAs have been completed, representing a completion rate of 65 per cent.

# Table 3 summarizes progress made by UNDP since 1991.

## Table 3: Progress made by UNDP since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes* |  |  | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 69,342 | 827,395 | 888,683,160 | 11.50 | 2,802 | 2,620 | 34 | 38 | 4 | 186 | 121 |

* HFC related projects.

HFC-related projects

# As of 31 December 2024, the Executive Committee had approved 117 HFC-related projects (including one demonstration project, 44 investment projects, 50 project preparation activities and 22 technical assistance projects) amounting to US $26,947,921 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 1 | 0 | 0 | 150,000 | 0 | 150,000 | 0 |
| Investment** | 44 | 5 | 11 | 19,125,234 | 6,937,477 | 12,187,757 | 36 |
| Project preparation | 50 | 33 | 66 | 4,689,011 | 3,024,432 | 1,664,579 | 65 |
| Technical assistance | 22 | 19 | 86 | 2,983,676 | 2,253,041 | 730,635 | 76 |
| Total | 117 | 57 | 49 | 26,947,921 | 12,214,950 | 14,732,971 | 45 |

* Excludes agency support costs.

** 2,605 mt (5,549,026 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2024, of the 117 projects, five investment projects, 33 project preparation and 19 technical assistance projects have been completed, leaving 60 ongoing. These activities are at various stages of implementation.

# Of the total cumulative funding approved of US $26,947,921 (excluding agency support costs), US $12,214,950 had been disbursed, representing a disbursement rate of 45 per cent.

Issues identified in project implementation in 2024

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 15 projects classified as projects with implementation delays (including 12 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); two technical assistance projects and one HFC investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 98th meeting.

# In addition, an issue has been identified regarding a tranche of an MYA for the phase-out of HCFCs. This issue is also presented in annex III. A brief description on the status of implementation and the outstanding issue are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Angola, Bangladesh, China (overarching, industrial and commercial refrigeration and air-conditioning, solvent), Cuba, Mali, Peru, and South Sudan, with the KIP for Mexico, and reports on projects with specific reporting requirements associated with Lebanon (HPMP), have been submitted to the 97th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 121 ongoing projects, excluding IS and project preparation, 16 projects have revised planned dates of completion since the 2023 progress report.

# In line with decision 95/12(b), the Secretariat noted that a renewal request of the IS project for China had not been submitted for the last three years; it is expected to be submitted in 2026.

# At its 95th meeting, in approving the second tranche of stage II of the HPMP for Georgia, the Executive Committee noted that UNDP would submit a report on the progress of regulations to prohibit the import and installation of HCFC-based equipment as part of its 2024 financial and progress report to be submitted at the second meeting in 2025. UNDP has reported that a study had confirmed that no new refrigeration and air-conditioning (RAC) units using HCFCs are being imported or offered for sale in the country. Stakeholders, including importers, service companies, and vocational training institutions, further validated that the market is gradually shifting toward systems based on low-global-warming-potential refrigerants, in alignment with global manufacturing trends and supply chain realities. UNDP will provide an update on the matter at the 97th meeting.

# In line with decision 82/11(b), UNDP has requested the extension of the duration of nine projects, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Disbursement (%) | Activities requiring additional time | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- |
| Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) |  |  |  |  |
| Zimbabwe ZIM/REF/82/INV/55 | 89 | Completion of prototype of the cooling circuits, commissioning of freezer line and safety audit completion | Jun-25 | Jun-26 |
| Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  |  |  |
| Chile CHI/DES/94/PRP/213 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Jun-26 | June-27 |
| Cuba CUB/DES/93/PRP/69 | 14 | Completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |
| Egypt EGY/DES/93/PRP/155 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |
| Jamaica JAM/DES/93/PRP/46 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |
| Panama PAN/DES/94/PRP/58 | 0 | Completion of data collection and analysis, and report preparation | June-26 | June-27 |
| Peru PER/DES/93/PRP/64 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |
| Trinidad and Tobago TRI/DES/93/PRP/43 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |
| Uruguay URU/DES/93/PRP/82 | 0 | Recruitment of consultant, completion of data collection and analysis, and report preparation | Dec-25 | Dec-26 |

Gender mainstreaming

# All projects implemented by UNDP continue to apply its Gender Equality Strategy, the gender mainstreaming policy of the Multilateral Fund and relevant national gender policies. In general, UNDP ensures that project implementation includes consultations with relevant associations, networks, and stakeholders, and disaggregated data collection on the participation of women. UNDP’s country offices monitor their performance on gender equality through the flagship Gender Seal programme, which measures progress across a range of criteria, including the impact of UNDP’s interventions at the country level. Although activities to promote women’s participation vary by country, the strategies deployed thus far have led to increased participation of women in training courses and meetings organized under the Montreal Protocol portfolio.

# In China, UNDP collaborated with the China Refrigeration and Air-conditioning Industry College Student Science and Technology Competition to engage youth and empower young women in sustainable practices within the refrigeration sector. This initiative promoted visibility, mentorship, and career development for young women, helping to address professional barriers in the sector. In Colombia, a nationwide data collection exercise was conducted to identify and profile women involved in the RAC sector. Subsequently, the annual meeting of women in the RAC sector was held, which focused on the signing of an expression of interest in the formation of the RAC Women’s Network in Colombia. In Mali, two sensitization workshops were held in Bamako, training 90 participants on best refrigeration practices and the importance of customs enforcement in ensuring the country’s compliance to the Montreal Protocol, with 21 women participating, representing 23 per cent of the total number of participants. The RAC technicians’ workshop achieved 34 per cent female participation. These outcomes reflect meaningful progress in inclusive capacity-building and provide a strong foundation for future gender-responsive programming in Mali.

# Finally, data collection for KIP preparation includes the number of technicians disaggregated by gender, sector and subsector. Furthermore, while developing KIPs and new stages of HPMPs, UNDP extensively considers lessons learned from previous HPMPs regarding gender mainstreaming. The key challenges include the lack of baseline data on gender and the limited involvement of women in the RAC sector.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 December 2024 contained in document UNEP/OzL.Pro/ExCom/97/13;

## To approve the extension of the completion dates of the projects listed below to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/97/13:

### To June 2026, for the conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) for Zimbabwe (ZIM/REF/82/INV/55);

### For the preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) for the following countries:

#### To December 2026, for Cuba (CUB/DES/93/PRP/69); Egypt (EGY/DES/93/PRP/155); Jamaica (JAM/DES/93/PRP/46); Peru (PER/DES/93/PRP/64); Trinidad and Tobago (TRI/DES/93/PRP/43); and Uruguay (URU/DES/93/PRP/82); and

#### To June 2027, for Chile (CHI/DES/94/PRP/213); and Panama (PAN/DES/94/PRP/58); and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER COUNTRY FOR 2024

# Table 1 of annex I presents the status of project implementation by country for 2024 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNDP for 2024

| Country | Phased out in 2024 (ODP tonnes)* | Phased out in 2024 (CO2-eq tonnes)* | Estimated funds disbursed in 2024 (US$) | Funds disbursed in 2024 (US$) | Percentage of funds disbursed over estimation in 2024 | Percentage of planned projects completed in 2024** |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 0.0 | 0 | 272,286 | 114,499 | 42 |  |
| Argentina | 0.0 | 0 | 185,128 | 92,933 | 50 |  |
| Bangladesh | 6.8 | 0 | 507,649 | 1,139,761 | 225 | 0 |
| Barbados | 0.0 | 0 | 28,750 | 0 | 0 |  |
| Belize | 0.0 | 0 | 21,325 | 0 | 0 | 100 |
| Bhutan | 0.0 | 0 | 25,000 | 0 | 0 | 0 |
| Brazil | 66.3 | 0 | 1,074,324 | 2,194,806 | 204 |  |
| Cambodia | 0.4 | 0 | 62,902 | 46,169 | 73 | 100 |
| Chile | 0.0 | 0 | 373,434 | 199,740 | 53 |  |
| China | 98.6 | 0 | 2,994,092 | 5,756,097 | 192 | 50 |
| Colombia | 0.0 | 0 | 623,325 | 559,150 | 90 |  |
| Costa Rica | 0.0 | 0 | 284,866 | 328,618 | 115 |  |
| Cuba | 0.0 | 0 | 304,597 | 283,308 | 93 | 100 |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 50,140 | 0 | 0 | 0 |
| Dominican Republic (the) | 0.0 | 0 | 365,427 | 132,036 | 36 | 100 |
| Egypt | 0.0 | 0 | 629,235 | 444,436 | 71 | 0 |
| El Salvador | 3.8 | 0 | 119,927 | 85,684 | 71 | 0 |
| Eswatini | 0.0 | 0 | 38,500 | 9,000 | 23 | 100 |
| Fiji | 0.0 | 0 | 119,976 | 16,421 | 14 | 0 |
| Georgia | 0.0 | 0 | 67,856 | 190,822 | 281 | 100 |
| Ghana | 0.0 | 0 | 187,006 | 206,505 | 110 | 100 |
| Grenada | 0.0 | 0 | 36,187 | 0 | 0 | 100 |
| Guyana | 0.0 | 0 | 67,103 | 13,250 | 20 | 0 |
| Haiti | 0.0 | 0 | 49,720 | 59,607 | 120 | 100 |
| India | 165.2 | 0 | 2,488,148 | 1,294,054 | 52 | 100 |
| Indonesia | 31.4 | 0 | 1,608,721 | 716,069 | 45 | 100 |
| Iran (Islamic Republic of) | 6.6 | 0 | 647,942 | 449,008 | 69 | 50 |
| Jamaica | 0.0 | 0 | 130,309 | 51,750 | 40 |  |
| Kyrgyzstan | 0.0 | 0 | 52,040 | 0 | 0 |  |
| Lao People's Democratic Republic (the) | 0.0 | 0 | 49,024 | 35,735 | 73 | 100 |
| Lebanon | 1.1 | 0 | 436,679 | 376,273 | 86 | 100 |
| Malaysia | 0.0 | 0 | 832,776 | 460,539 | 55 | 100 |
| Maldives | 0.0 | 0 | 35,000 | 22,026 | 63 | 100 |
| Mali | 0.0 | 0 | 51,440 | 0 | 0 | 0 |
| Mexico | 0.0 | 0 | 482,008 | 151,580 | 31 | 100 |
| Mozambique | 0.0 | 0 | 73,650 | 18,509 | 25 | 0 |
| Nepal | 0.1 | 0 | 19,104 | 40,685 | 213 | 100 |
| Nigeria | 17.4 | 0 | 971,210 | 1,188,161 | 122 | 100 |
| Pakistan | 0.0 | 0 | 171,334 | 42,215 | 25 |  |
| Panama | 0.0 | 0 | 293,803 | 203,384 | 69 | 100 |
| Paraguay | 0.7 | 0 | 30,073 | 48,255 | 160 |  |
| Peru | 2.0 | 0 | 449,263 | 270,583 | 60 |  |
| Philippines (the) | 0.0 | 0 | 220,000 | 94,567 | 43 | 0 |
| Republic of Moldova (the) | 0.2 | 0 | 12,645 | 36,968 | 292 | 100 |
| South Sudan | 0.0 | 0 | 21,500 | 0 | 0 | 0 |
| Sri Lanka | 0.8 | 0 | 210,775 | 375,007 | 178 | 67 |
| Timor-Leste | 0.1 | 0 | 1,260 | 0 | 0 | 100 |
| Trinidad and Tobago | 0.0 | 0 | 693,670 | 375,125 | 54 | 100 |
| Türkiye | 0.0 | 0 | 72,242 | 56,837 | 79 | 100 |
| Uruguay | 0.0 | 0 | 760,736 | 235,971 | 31 | 100 |
| Venezuela (Bolivarian Republic of) | 0.0 | 0 | 169,760 | 68,018 | 40 |  |
| Zimbabwe | 0.0 | 0 | 194,189 | 261,973 | 135 | 50 |
| Global*** | 0.0 | 0 | 0 | 0 |  | 100 |
| Grand total | 401.5 | 0 | 19,668,056 | 18,746,134 | 95 | 72 |

* No phase-out in 2024 for HFC-related projects.

** For projects that were planned to be completed in 2024.

*** 2024 core unit.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER YEAR AS AT 31 DECEMBER 2024

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2017 have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,149,032 | 1,149,032 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,481,581 | 49,481,581 | 0 | 100 |
| 1995 | 117 | 117 | 100 | 29,599,446 | 29,599,446 | 0 | 100 |
| 1996 | 83 | 83 | 100 | 27,838,805 | 27,838,805 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 44,056,257 | 44,056,257 | 0 | 100 |
| 1998 | 172 | 172 | 100 | 31,305,010 | 31,305,010 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,896,884 | 35,896,884 | 0 | 100 |
| 2000 | 149 | 149 | 100 | 31,268,361 | 31,268,361 | 0 | 100 |
| 2001 | 179 | 179 | 100 | 35,292,271 | 35,292,271 | 0 | 100 |
| 2002 | 117 | 117 | 100 | 44,316,422 | 44,316,422 | 0 | 100 |
| 2003 | 64 | 64 | 100 | 36,336,530 | 36,336,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,802,714 | 24,802,714 | 0 | 100 |
| 2005 | 53 | 53 | 100 | 29,124,833 | 29,124,833 | 0 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,458 | 15,753,459 | -1 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,486 | 12,142,486 | 0 | 100 |
| 2008 | 84 | 84 | 100 | 22,873,866 | 22,873,866 | 0 | 100 |
| 2009 | 92 | 92 | 100 | 13,217,903 | 13,217,903 | 0 | 100 |
| 2010 | 43 | 43 | 100 | 19,567,970 | 19,567,970 | 0 | 100 |
| 2011 | 63 | 63 | 100 | 57,415,931 | 57,415,931 | 0 | 100 |
| 2012 | 29 | 29 | 100 | 33,818,922 | 33,818,922 | 0 | 100 |
| 2013 | 43 | 43 | 100 | 33,958,972 | 33,958,972 | 0 | 100 |
| 2014 | 67 | 67 | 100 | 22,560,966 | 22,561,030 | -64 | 100 |
| 2015 | 75 | 75 | 100 | 30,256,568 | 30,274,905 | -18337 | 100 |
| 2016 | 52 | 52 | 100 | 41,574,769 | 41,536,980 | 37,789 | 100 |
| 2017 | 43 | 43 | 100 | 35,237,535 | 35,118,103 | 119,432 | 100 |
| 2018 | 62 | 61 | 98 | 40,667,384 | 39,088,774 | 1,578,610 | 96 |
| 2019 | 41 | 37 | 90 | 10,322,186 | 9,689,496 | 632,690 | 94 |
| 2020 | 50 | 46 | 92 | 29,795,896 | 27,100,573 | 2,695,323 | 91 |
| 2021 | 66 | 55 | 83 | 24,642,528 | 20,393,289 | 4,249,239 | 83 |
| 2022 | 38 | 23 | 61 | 13,768,300 | 6,537,652 | 7,230,648 | 47 |
| 2023 | 81 | 9 | 11 | 34,974,872 | 5,151,863 | 29,823,009 | 15 |
| 2024 | 75 | 0 | 0 | 32,674,861 | 189,126 | 32,485,735 | 1 |
| Total | 2,802 | 2,620 | 94 | 967,517,233 | 888,683,160 | 78,834,073 | 92 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Barbados BAR/PHA/91/INV/33 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) DRC/PHA/88/INV/49 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| El Salvador ELS/PHA/91/TAS/45 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Fiji FIJ/PHA/88/INV/39 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 and 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Fiji FIJ/PHA/92/TAS/44 | Verification report on the implementation of the HCFC phase-out management plan | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Guyana GUY/PHA/83/INV/32 | HCFC phase-out management plan (stage II, second tranche) | 20 | Administrative delays in procurement | To request UNDP to submit a status report to the 98th meeting on implementation progress |
| Guyana GUY/PHA/92/INV/36 | HCFC phase-out management plan (stage II, third tranche) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| India IND/PHA/91/INV/495 | HCFC phase-out management plan (stage III, first tranche) (air-conditioning manufacturing sector) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| India IND/PHA/91/INV/498 | HCFC phase-out management plan (stage III, first tranche) (servicing sector) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| India IND/PHA/91/INV/500 | HCFC phase-out management plan (stage III, first tranche) (Technical assistance for MSMEs) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Indonesia IDS/PHA/92/INV/222 | HCFC phase-out management plan (stage III, first tranche) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/86/INV/245 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/92/INV/266 | HCFC phase-out management plan (stage II, fourth tranche) (commercial refrigeration sector) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/92/INV/267 | HCFC phase-out management plan (stage II, fourth tranche) (foam sector) | 0 | 18 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Sri Lanka SRL/PHA/86/INV/58 | HCFC phase-out management plan (stage II, first tranche) | 23 | 12 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |
| Zimbabwe ZIM/REF/82/INV/55 | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | 89 | 12 months delays | To request UNDP to report to the 98th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/97/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 97th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 97th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2024. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2024.

Including 2,605 mt of HFC-related projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/97/35

UNEP/OzL.Pro/ExCom/97/37

UNEP/OzL.Pro/ExCom/97/44

UNEP/OzL.Pro/ExCom/97/46

UNEP/OzL.Pro/ExCom/97/58

UNEP/OzL.Pro/ExCom/97/70

UNEP/OzL.Pro/ExCom/97/78

UNEP/OzL.Pro/ExCom/97/60

UNEP/OzL.Pro/ExCom/97/17

Decision 95/34(a), annex XVII of UNEP/OzL.Pro/ExCom/95/94

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.